## CR Log
CR ID | Date Submitted | Client Name | Submitted By | Description | Category | Severity | Status | Assigned To | Quote (NIS) | Approved Date | Delivered Date | Closed Date | Resolution Days | Billable? | Amount Billed (NIS) | Notes
CR-001 | 2026-07-10 | Giliguli | Eden David | Change date format on revenue chart from DD/MM to MM/YYYY | Minor Adjustment | P4 - Low | Closed | Arye |  | 2026-07-10 | 2026-07-10 | 2026-07-10 |  | No |  | Quick fix, 10 min
CR-002 | 2026-07-12 | Studio Flex | Yael Cohen | Add class utilization heatmap by day/hour | KPI / Data Change | P3 - Medium | Delivered | Arye |  | 2026-07-12 | 2026-07-15 |  |  | No |  | Within monthly quota
CR-003 | 2026-07-14 | Giliguli | Eden David | Add automated weekly email report with KPI summary | Feature Addition | P4 - Low | Quoted | Ofir | 800 |  |  |  |  | Yes |  | Quote sent, awaiting approval
CR-004 | 2026-07-15 | Tech Solutions Ltd | Moshe Levy | Dashboard not loading - API connection timeout | Minor Adjustment | P1 - Critical | In Progress | Arye |  | 2026-07-15 |  |  |  | No |  | Scalla API intermittent issue

## Dashboard
CR Management Dashboard
Total CRs | Open CRs | Avg Resolution (days) | Billable Revenue (NIS) | CRs This Month | SLA Compliance %
By Category |  |  | By Status
Minor Adjustment |  |  | Submitted
KPI / Data Change |  |  | Triaged
Feature Addition |  |  | Quoted
Structural Rebuild |  |  | Approved
In Progress
Delivered
Closed
Cancelled

## SLA Reference
Severity | Definition | Response SLA | Resolution SLA
P1 - Critical | Dashboard down, data incorrect, security issue | Same business day | 24 hours
P2 - High | Major feature broken, key KPI not updating | 1 business day | 3 business days
P3 - Medium | Minor feature issue, cosmetic problem | 2 business days | 5 business days
P4 - Low | Enhancement request, nice-to-have | 3 business days | Next maintenance cycle (30 days)
Pricing Reference
Category | Pricing Rule
Minor Adjustment | Included in monthly maintenance (unlimited)
KPI / Data Change | 2/month included; 200 NIS each beyond quota
Feature Addition | Quoted individually (typically 500-1,500 NIS)
Structural Rebuild | Quoted as mini-project (typically 1,500-3,000 NIS)
Rush Delivery | 50% surcharge on quoted price
Pre-paid Bundle | 5 KPI changes for 800 NIS (20% discount)